Goal: Deliver ICMS 3.0 at Team Leaders meeting 2025

Waypoints:

- Present proposed ICMS 3.0 mock-ups and changes to supporting systems at TL 2024

- Review and engage with changes to Virtual OSOCC (VO) – linking ICMS + VO?!

- Get Sponsorship for Develops (AE, JH)

- Select additional developers as required (determined by AE, JH)

Work to be done:

- Develop and confirm data capture requirements (Qatar)

- Confirm and present new form structures, Data and Format:

  - Triage

  - Worksite

  - Victim Extrication

  - Logistics request

  - Team Fact sheet

  - Medical Handover form!?

- Process

  - Delinking of worksite ID’s from sectors (we may need have a sector linking function but as an option rather than hardwired)

  - Align mobilisation terms across all platforms (TWG Checklist)

  - Coordination Layers and how we ID them (Sector, Segment, Worksite AOI/POI)

- Develop forms:

  - Triage

  - Worksite

  - Victim extrication

- System

  - Move to Quick Capture and Field maps.

  - Move to experience builder for Dashboards??

  - Tasking functions (Work Force)

  - Dashboard rebuilds. (EB)

  - Reporting

  - VO enhancements and linking.

- Apps:

  - Develop SARCOP modelled ICMS 3.0 Field app within Quick Capture/Field Maps

- Training:

  - Develop training materials.

  - Develop Training plan.

  - Deliver timeline for training (ToT)?!!

- Recruiting

  - Developers

  - Endorsed members.

  - Advisor members

Timelines:

Present proposed ICMS 3.0 mock-ups and changes to supporting systems at TL 2024.

- Work Required

  - Data set completed.

  - Form design completed. (Simplified)

  - Worksite ID modelling agreed on.

  - Coordination Layers agreed on.

  - Field app - Quick capture design agreed on – Mocked up.

  - Dashboard Design and content agreed on – Mocked up.

  - Tasking methodology agreed and mocked up

  - Reporting – Outputs agreed and mocked up

VO Enhancements.

- Alignment of Team Status (All applications

- VO to only be a one-way comms for coordination function (out)

- Incoming info from teams via an agreed path – not VOSOCC

- Work with VO people to get alignment

Develop project Gantt charts and task assignments

Sponsorship:

- Aidan, Ed and John H need to be sponsored to attend at least one of the IMWG meetings each year. (Neither home agency is able to provide the needed sponsorship.

- Primary approach INSARAG Sec to get funding for 1-2 trips per year for both

- Key risk is that we will not be able to progress to ICMS 3.0 without this.

- This is a priority action